## Charter Example
PROJECT DESCRIPTION
Error-proof the hardware packaging operations to reduce the missing hardware rate from 3.3% to 1.2%. Error proofing will be accomplished by adding three new hardware packing stations to replace the existing manual stations.
BUSINESS NEED
(1) Missing hardware is an ongoing issue that affects customer satisfaction (2) the customer service team spends approximately $80K/yr in dealing with missing parts (customer calls, shipping costs, etc.)
OWNERSHIP & APPROVAL
Project Manager | Bob Thou |  | Project Champion | Bob Demorest |  | Approval Date | Pending
Project Number | PR210
FINANCIALS & MILESTONES
Financials |  |  | Capital/Expense |  |  | Milestones (Schedule)
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Initial Investment | 150000 |  | Expense - 5 yr service contract for equip and leased data storage | 300000 |  | Equipment Design | 2012-02-15
Net Present Value (5 yr) | 430797.1646 |  |  |  |  | Quotations / Equip Builder Select | 2012-03-01
ROI | 123.5% |  | Capital | 425000 |  | Equip Sign-Off | 2012-05-15
IRR | 57.39% |  | Expense - 5 yr equipment lease | 1000000 |  | Installation | 2012-06-01
RESOURCES & RISKS
Internal Resources |  |  | External Services |  |  | Project Risks
| Total Hours | Peak Hrs/Wk |  | Budget | Actual |  | Medium | High
John Smith (Design) | 90 | 40 | Equip Builder (TBD) | 55000 |  | Technical Feasibility |  | ü
Mike Gorman (Design) | 10 | 2 | Other |  |  | Floor Space | ü
David Stone (Mkt Comm.) | 15 | 2 | Other
Louis Clemens (A.M.E.) | 5 | 2 | Other
Alan Carr (Sourcing) | 20 | 8 | Other

## Financials Example
Financial Benefits and Costs
Note - review with your finance team to ensure accurate assumptions and calculations
Cost of Capital | 8% | (see finance team for updated value)
Initial Cost of Project | 150000
Cash Inflows | Months | 0 | 1 | 2 | 3 | 4 | 5
Incremental Revenue * Margin |  |  | 0 | 0 | 0 | 0 | 0
Material Cost Savings
Labor Savings (Extra hours) |  |  | 0 | 0 | 80000 | 80000 | 80000
Supplies |  |  | 0 | 25000 | 25000 | 25000 | 25000
Time out to cash |  |  | 0 | 150000 | 180000 | 180000 | 180000
Cash Inflow |  |  | 0 | 175000 | 285000 | 285000 | 285000
Present Value of Cash Inflow |  |  | 0 | 150034.2936 | 226242.1887 | 209483.508 | 193966.2112
Cumulative Cash Inflow |  |  | 0 | 150034.2936 | 376276.4822 | 585759.9903 | 779726.2014
Costs
Initial Investment |  | 150000
Machinery restoration |  |  | 0 | 0 | 150000 | 0 | 0
Maintenance PM |  |  | 0 | 0 | 0 | 0 | 0
Operator Training |  |  | 20000 | 20000 | 20000 | 20000 | 20000
Other
Cash Outflow |  | 150000 | 20000 | 20000 | 170000 | 20000 | 20000
PV of Cash Outflow |  | 150000 | 18518.5185 | 17146.7764 | 134951.481 | 14700.5971 | 13611.6639
Cumulative Cash Outflow |  | 150000 | 168518.5185 | 185665.2949 | 320616.7759 | 335317.373 | 348929.0369
NPV of Project | 430797.1646
IRR | 57.39%
ROI | 123.5%
Year |  | 0 | 1 | 2 | 3 | 4 | 5
Cash Flow |  | -150000 | -20000 | 155000 | 115000 | 265000 | 265000

## Instructions - Charter
visit www.dmaictools.com for more instructions / training
PROJECT DESCRIPTION
Error-proof the hardware packaging operations to reduce the missing hardware rate from 3.3% to 1.2%. Error proofing will be accomplished by adding three new hardware packing stations to replace the existing manual stations.
BUSINESS NEED
(1) Missing hardware is an ongoing issue that affects customer satisfaction (2) the customer service team spends approximately $80K/yr in dealing with missing parts (customer calls, shipping costs, etc.)
OWNERSHIP & APPROVAL
Project Manager | Bob Thou |  | Project Champion | Bob Demorest |  | Approval Date | Pending
Project Number | PR210
FINANCIALS & MILESTONES
Financials |  |  | Capital/Expense |  |  | Milestones (Schedule)
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Initial Investment | 150000 |  | Expense - 5 yr service contract for equip and leased data storage | 300000 |  | Equipment Design | 2012-02-15
Net Present Value (5 yr) | 430797.1646 |  |  |  |  | Quotations / Equip Builder Select | 2012-03-01
ROI | 123.5% |  | Capital | 425000 |  | Equip Sign-Off | 2012-05-15
IRR | 57.39% |  | Expense - 5 yr equipment lease | 1000000 |  | Installation | 2012-06-01
Resources & Project Risks
Internal Resources |  |  | External Services |  |  | Project Risks
| Total Hours | Peak Hrs/Wk |  | Budget | Actual |  | Medium | High
John Smith (Design) | 90 | 40 | Equip Builder (TBD) | 55000 |  | Technical Feasibility |  | ü
Mike Gorman (Design) | 10 | 2 | Other |  |  | Floor Space | ü
David Stone (Mkt Comm.) | 15 | 2 | Other
Louis Clemens (A.M.E.) | 5 | 2 | Other
Alan Carr (Sourcing) | 20 | 8 | Other
A
Briefly describe the project and note the financial or other benefits.
A
B
B
Describe why the project is needed, i.e. sales growth, productivity, problem resolution
C
C
The project manager leads the project from beginning to end. The project champion is a high level or otherwise influential person that supports the project.
D
D
These values can be found in the financials tab. Color code as needed to show acceptable or unacceptable financial metrics.
E
E
Note the major funding needs for the project, including capital expenditures and expenses that are outside of the normal budget.
F
F
These are the completion dates for major project milestones. The last date should reflect the completed project.
G
Note the in-house support time that will be needed from various functions. Doing this will avoid having to "beg" for help later.
G
H
H
This section includes any outside services that will be required, along with the planned spend.
I
This section includes any outside services that will be required, along with the planned spend.
I

## Instructions - Financials
Financial Benefits and Costs
Note - review with your finance team to ensure accurate assumptions and calculations
Cost of Capital | 8% | (see finance team for updated value)
Initial Cost of Project | 425000
Cash Inflows | Year | 0 | 1 | 2 | 3 | 4 | 5
Incremental Revenue * Margin |  |  | 200000 | 200000 | 200000 | 200000 | 200000
Material Cost Savings
Labor Savings |  |  | 80000 | 80000 | 80000 | 80000 | 80000
Other Savings - Warranty |  |  | 350000 | 420000 | 550000 | 400000 | 200000
Other
Cash Inflow |  |  | 630000 | 700000 | 830000 | 680000 | 480000
Present Value of Cash Inflow |  |  | 583333.3333 | 600137.1742 | 658880.76 | 499820.2999 | 326679.9346
Cumulative Cash Inflow |  |  | 583333.3333 | 1183470.5075 | 1842351.2676 | 2342171.5675 | 2668851.5021
Costs
Initial Investment |  | 425000
Equipment Service Contract |  |  | 50000 | 50000 | 50000 | 50000 | 50000
Incremental Data Storage |  |  | 10000 | 10000 | 10000 | 10000 | 10000
Equipment Lease |  |  | 200000 | 200000 | 200000 | 200000 | 200000
Other
Cash Outflow |  | 425000 | 260000 | 260000 | 260000 | 260000 | 260000
PV of Cash Outflow |  | 425000 | 240740.7407 | 222908.0933 | 206396.3827 | 191107.7617 | 176951.6312
Cumulative Cash Outflow |  | 425000 | 665740.7407 | 888648.834 | 1095045.2167 | 1286152.9784 | 1463104.6096
NPV of Project | 1205746.8924
IRR | 93.61%
ROI | 82.41%
Year |  | 0 | 1 | 2 | 3 | 4 | 5
Cash Flow |  | -425000 | 370000 | 440000 | 570000 | 420000 | 220000
A
A
This is the cost of capital for the business and should be supplied by the finance or accounting team
B
B
Note the up-front cost for the project - this is normally spent in "year zero" and includes both capital and expense items.
B
C
C
These are the financial benefits that the project will generate for the next five years. Adjust the row headings as needed.
D
D
Note any ongoing costs that will offset the financial benefits in (C). Adjust the row headings as needed.
E
These are the calculated financial benefits for the project that match the values in the charter page.
E
This chart shows the net cash flow by year, based on items (C) and (D).
F
F